## Project Schedule
Gantt Chart
| Color Code | Team Menbers
|  | 1 | Atinder Singh
|  | 2 | Mohit
|  | 3 | Lovepreet Singh
[5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
TASK LIST |  |  |  | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  | Hours
1 | Planning & Research |  |  |  | 3 | 4 | 5 | 8 | 8 | [23 empty] | Week1 | 28
| 1.1 Read Assessment 1.2 Divide Roles 1.3 Research about agile Methodology 1.4 Research About Project |  |  |  | 2 | 8 | 5 | 8 | 8 | [24 empty] | 31
[6 empty] | 2 | 5 | 8 | 8 | . | [23 empty] | 23
0
0
2 | Revission | [32 empty] | 0
| 2.1 Decide Topic 2.2 Discussion About Layouts 2.3 Start Making Wireframes 2.4 Discussion About Backend | [10 empty] | 6 | 4 | 7 | 8 | 8 | [16 empty] | Week2 | 33
[12 empty] | 5 | 8 | 5 | 8 | 8 | [17 empty] | 34
[12 empty] | 7 | 2 | 4 | 8 | 8 | [17 empty] | 29
0
3 | Source/Startup | [32 empty] | 0
| 3.1 Select Source/Github 3.2 Make repo and invite 3.3 Work on Layouts 3.4 Work on Backend | [18 empty] | 8 | 4 | 3 | 8 | 8 | 8 | 8 | [6 empty] | Week3 | 47
[20 empty] | 7 | 6 | 5 | 8 | 8 | 8 | 8 | [7 empty] | 50
[20 empty] | 6 | 6 | 5 | 8 | 8 | 8 | 8 | [7 empty] | 49
0
0
4 | Working And Finishing | [32 empty] | 0
| 4.1 Making Prototype 4.2 Question/ Answers 4.3 Making Ducomentstion file 4.4 Check Project /Upload on github | [27 empty] | 8 | 8 | 8 | 8 | Week4 | 32
[29 empty] | 5 | 8 | 8 | 8 |  | 29
[29 empty] | 8 | 8 | 8 | 8 |  | 32
0

## Project Documentation
Documentation
Agile Group Project
Purpose
The purpose of the assessment is to create an Android App using Agile and Scrum methodologies. We are team of three persons for making a application usiong Agile And Scrum Methodologies. Firstly we research about the Agile and Scrum.Afterthat we choose a application content . We choose E-Commerce application in xamarin forms. We know its very hard and challaging for us but we work as a team. We choose a application name that is Watch shop . We decide to make a application on watch shop .Where peoiple can buy various types of watches . So It is a E commerce appliction . I will discuss some functionailties and some other part of the application below .
Functionalities
We make E-Commerce application . There are some functions… 1.Show Details = If some one click on any product user can see products in the first page. Where user can see details like price and specification of the products . And there have button for add to cart which is redirect to next page. 2. Add to cart = if someone click on Add to cart button page will redirect to next page where product stored in wishlist but unfortunately this function is not working yet . we will continue in further project.

## Individual Question Answers
Question/Answers
Agile And Scrum
| Q1 | What was the App that your group created?
| Answer | We Create E-Commerce Application in Xamrain Froms by using agile methodology.
| Q2 | What did you learn about how the Agile and Scrum methodologies operate?In practice how effective did you find this methodology?
| Answer | In short, scrum refers to a framework that makes for effective collaborations among teams that are working on complex products..Agile scrum methodology has several benefits. First, it encourages products to be built faster, since each set of goals must be completed within each sprint's time frame.
| Q3 | What did you find was the strength of it?
| Answer | High customer satisfaction . High flexibility of the project.
| Q4 | What were its weaknesses?
| Answer | Lack of long-term planning. Difficult planning at early stages.
| Q4 | What were the best features of the process?
| Answer | 1. Agile development releases and fixed-length iterations 2. Continuous (adaptive) planning
| Q5 | How did they appeal to you?
| Answer | Planning : Planning helps to make a project with easy ways also save time.
| Q6 | What was the worst feature of the process ?
| Answer | Less predictability. More time and commitment.
| Q7 | How would you change them?
| Answer | work with plan. Divide work with team members.
Group Work
| Q1 | What did you enjoy about this style of programming?
| Answer | I enjoy agile program with my team members. We work together in the class and on live meetings .I enjoy this project because my team member contribute very well.
| Q2 | What are the downsides for you of group work?
| Answer | No Downsides for our group work
| Q3 | How did this session change your opinion of working in industry?
| Answer | Initiallly I think its very hard to make a Project for one person when I was unknown about agile methodology . After that , my thinking is totatlly changed about this because with the help of team members by agile and other similar platforms , work easily done .
Source Control
| Q1 | What form of Source Control did you use?
| Answer | We are using GitHub . We create a common reporistory in team and push code time to time .
| Q2 | What were its strengths?
| Answer | It makes it easy to contribute to your open source projects. Share repositary by make team and work together in one project.
| Q3 | What were its weekness?
| Answer | Sometime face problem to push code in same repositary. No backup .
| Q4 | How effective as a source control did you find it?
| Answer | We are using github from a year . Our tutor told us about this . Commit , push and pull . These are very effective in a github
| Q4 | If you had to use it again what would you change?
Answer

## Daily Meeting
Daily Meeting
We communicate with each other by Phone calls, Team Messages and Team Meetings whenever we need any help or when our team member stuck somewhere . |  | Most of the works we done in the class time. We always sit together and Do works.
Class Work
Communication

## Wirefarmes
Wire Farmes
First Picture
First Wirefarame shows main page of the application . Where all the products shows in the cards and details of the product.There are some icons also describe some functionailty like add to cart icon shows whichlist. If someone click on product , full infomation like specifications of the product show in next page.
Second Picture
Second wireframe shows the product detail page in the application .in this page user can see detail of particular product like price , specifications and about product. And there have add to cart button in the bottom this page from where user can choose this product and add into cart for further process.
Third Picture
Third wireframe shows about wishlists .All the products appers in the add to cart section which was selected by users. After adding user can proccess their order by doing payment method .

## Usablity Testing
Usablity Testing
| Test Cases |  | Result | Description |  | Error
| Loading Products |  | Pass | Poducts Loaded Successfully |  | X
| Loading Icons |  | Pass | All icons Appear |  | X
| Click Functions |  | Pass | Some Click events Work |  | X
| User-Friendly |  | Pass | Appication is User Friendly to use |  | X
| Pages |  | Pass | Some pages not work |  | X
Tests | Agree | Neutral | Unsure | Disagree | Comments
Usabality
Project is running without errors
Products are loaded Successfully
All Pages Are working correctlly |  |  |  |  | Some Pages are not woring because I did npot done their functionailty yet my pplan is to doing this in next project
Readablity
All the icons appear in the pages
Colour contrast matching with application
Size of the images, Font size and readablity ,is it user-friendly
Functionailty
Click on burger menu and see menu
Click on product image and see details
Add product into wishlist |  |  |  |  | Some functions are not woring because I did not done their functionailty yet my plan is to doing this in next project
Fittness Of purpose
Project is relevent content with their purpose
All documentations are ready

## UI Prototype
Ui Prototype
Step 1 |  | Step 2 | Step3

## Presentation
Presentation
What Agile Development Is?
It is considered both a Philosphy and a Method for building and releasing products .It is intended for teams anywhere 2 to 10 people. It is a Philosphy that aims to not only make you more organized and time aware, but more importantly aims to turn group into a team. It is about making your team a stronger and more dependable source.
Agile Development - Basics
1.Planning: Projects Manager Works with Team lead and client to determine requirements and scope .This helps us know what you'r building before you start. 2.Scrums: Daily 15 to 20 minute meetings to discuss yesterday and today.Group communication keeps team.